## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-001 | Read PDF documents with PyMuPDF | Must Have | None | Sumanth | Completed
Sprint 1 | Sprint 1 | US-002 | Read DOCX documents using python-docx | Must Have | US-001 | Sumanth | Completed
Sprint 1 | Sprint 1 | US-003 | Read TXT and CSV documents and normalize extracted text | Must Have | None | Sumanth | Completed
Sprint 1 | Sprint 1 | US-004 | Split extracted text into overlapping chunks | Must Have | US-001 | Sumanth | Completed
Sprint 1 | Sprint 1 | US-005 | Generate sentence-transformer embeddings | Must Have | US-004 | Sumanth | Completed
Sprint 1 | Sprint 1 | US-006 | Persist chunks and metadata in ChromaDB | Must Have | US-005 | Sumanth | Completed
Sprint 1 | Sprint 1 | US-007 | Build initial React dashboard and document upload workflow | Must Have | US-001 | Sumanth | Completed
Sprint 2 | Sprint 2 | US-008 | Classify queries as factual, procedural, comparative or ambiguous | Must Have | US-006 | Sumanth | Completed
Sprint 2 | Sprint 2 | US-009 | Retrieve relevant chunks with Top-1/Top-3/Top-5 control | Must Have | US-006 | Sumanth | Completed
Sprint 2 | Sprint 2 | US-010 | Generate grounded responses using configured Groq model | Must Have | US-009 | Sumanth | Completed
Sprint 2 | Sprint 2 | US-011 | Orchestrate query understanding, retrieval and response agents | Must Have | US-008 | Sumanth | Completed
Sprint 3 | Sprint 3 | US-012 | Ask clarification questions for vague or incomplete queries | Must Have | US-011 | Sumanth | Completed
Sprint 3 | Sprint 3 | US-013 | Resolve follow-up questions using conversation memory | Must Have | US-011 | Sumanth | Completed
Sprint 3 | Sprint 3 | US-014 | Add browser speech recognition and text-to-speech | Should Have | US-007 | Sumanth | Completed
Sprint 3 | Sprint 3 | US-015 | Show sources, supporting evidence and confidence in the UI | Must Have | US-009 | Sumanth | Completed
Sprint 4 | Sprint 4 | US-016 | Record query events and resolution outcomes in analytics storage | Must Have | US-011 | Sumanth | Completed
Sprint 4 | Sprint 4 | US-017 | Expose analytics summary, statistics, query history and knowledge gaps | Must Have | US-016 | Sumanth | Completed
Sprint 4 | Sprint 4 | US-018 | Display analytics data on the dashboard | Must Have | US-017 | Sumanth | Completed
Sprint 4 | Sprint 4 | US-019 | Improve sentence-aware chunking and validate ingestion | Must Have | US-004 | Sumanth | Completed
Sprint 4 | Sprint 4 | US-020 | Optimize retrieval and ambiguous-query routing using regression tests | Must Have | US-019 | Sumanth | In Progress
Sprint 4 | Sprint 4 | US-021 | Run end-to-end tests across Education, Technology and AI domains | Must Have | US-020 | Sumanth | In Progress
Sprint 4 | Sprint 4 | US-022 | Prepare technical guide, final report and demonstration checklist | Must Have | US-021 | Sumanth | Pending

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1 BACKLOG
US-001 | TS-01 | Implement PDF extraction with PyMuPDF |  |  | Sumanth | Development | Completed | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TS-02 | Implement DOCX paragraph extraction |  |  | Sumanth | Development | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | TS-03 | Implement TXT/CSV reading and text normalization |  |  | Sumanth | Development | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | TS-04 | Implement 500-character chunking with overlap |  |  | Sumanth | Development | Completed | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | TS-05 | Generate embeddings and validate dimensions |  |  | Sumanth | Development | Completed | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | TS-06 | Store chunks, source names and metadata in ChromaDB |  |  | Sumanth | Database | Completed | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | TS-07 | Build document upload and dashboard UI |  |  | Sumanth | UI Design | Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-008 | TS-08 | Implement query type classification |  |  | Sumanth | Development | Completed | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | TS-09 | Implement Top-K semantic retrieval and threshold filtering |  |  | Sumanth | Development | Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | TS-10 | Integrate grounded response generation |  |  | Sumanth | Development | Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | TS-11 | Implement multi-agent orchestration and API response payload |  |  | Sumanth | Development | Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-012 | TS-12 | Implement clarification behavior and multi-part query handling |  |  | Sumanth | Development | Completed | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-013 | TS-13 | Implement session-based follow-up memory |  |  | Sumanth | Development | Completed | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | TS-14 | Integrate Web Speech API voice input and TTS |  |  | Sumanth | UI Design | Completed | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-015 | TS-15 | Display sources, evidence, relevance and confidence |  |  | Sumanth | UI Design | Completed | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US-016 | TS-16 | Implement JSON analytics event storage |  |  | Sumanth | Development | Completed | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-017 | TS-17 | Add analytics summary/statistics/query/gap API routes |  |  | Sumanth | Development | Completed | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-018 | TS-18 | Connect dashboard analytics to API data |  |  | Sumanth | UI Design | Completed | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-019 | TS-19 | Improve sentence-aware chunking and test boundaries |  |  | Sumanth | Testing | Completed | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-020 | TS-20 | Diagnose RAG procedural retrieval and ambiguous routing failures |  |  | Sumanth | Testing | In Progress | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-021 | TS-21 | Run three-domain regression tests and record results |  |  | Sumanth | Testing | In Progress | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-022 | TS-22 | Complete documentation, report and final demo checklist |  |  | Sumanth | Documentation | Pending | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Daily | PDF/DOCX/TXT/CSV parsing differences | Validated each supported file type and normalized extracted text.
Sprint 1 | Daily | Chunk boundaries could split text unexpectedly | Added text cleanup and tested chunk output.
Sprint 2 | Daily | Queries needed intent-aware routing | Added factual, procedural, comparative and ambiguous classification.
Sprint 2 | Daily | Retrieval could return weak or irrelevant matches | Applied retrieval thresholds and tested Top-K behavior.
Sprint 3 | Daily | Vague follow-ups needed clarification and context | Implemented clarification and session-based memory; tested follow-up questions.
Sprint 3 | Daily | Browser voice APIs may fail due to permission/support | Added graceful voice handling; manual typing remains available.
Sprint 4 | Daily | Analytics needed to reflect actual interactions | Added analytics storage and summary/statistics/knowledge-gap endpoints.
Sprint 4 | Daily | RAG procedural paraphrase still misses relevant evidence | Logged as an open M4.3 issue; inspect raw distances and indexed chunks before tuning.
Sprint 4 | Daily | Full-app ambiguous routing needs regression check | Individual agents pass direct tests; validate end-to-end API behavior.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 |  |  | Sumanth | Write ingestion and chunking tests alongside implementation | Assuming every document format behaves identically | Validate PDF/DOCX/TXT/CSV ingestion | Tested supported file formats and improved text normalization
2 | Sprint 2 |  |  | Sumanth | Test retrieval with multiple query phrasings | Changing thresholds without inspecting evidence | Keep source attribution and no-answer behavior grounded | Introduced Top-K selection and retrieval threshold checks
3 | Sprint 3 |  |  | Sumanth | Test multi-turn context and clarification in the full application | Relying only on isolated agent tests | Preserve session IDs and graceful voice fallback | Follow-up memory and voice functionality were manually tested
4 | Sprint 4 |  |  | Sumanth | Record analytics and test outcomes during development | Claiming fixes or accuracy without evidence | Use regression tests across all three domains | Analytics dashboard/API added; retrieval and routing issues tracked as open